## Sheet1
Saeed Mohagheghi |  |  |  |  | Paid
Bronchoscopy Project |  |  |  |  | Not Paid
خرداد 98 | Activity | Hours |  | Tasks Done
| * Reading Docs | 5 |  | • Preparing Python + QT Framework
| * Example Codes | 6 |  | • Main App Initial GUI Design (Python + QT)
| * Main App GUI | 14
| * Tracker Connection | 5
| * Meetings @Parsiss | 4
| • Total Hours | 34
|  | @Parsiss | 9
|  | @Home | 25
تیر 98 | Activity | Hours |  | Tasks Done
| * Reading Docs | 6 |  | • Connection to Tracker (Polaris)
| * Main App GUI | 14 |  | • Load and Visualize Medical Images (mhd)
| * Tracker Connection | 23 |  | • Test Tracker in Linux (Ubuntu)
| * Meetings @Parsiss | 2
| • Total Hours | 45
|  | @Parsiss | 29
|  | @Home | 16
مرداد 98 | Activity | Hours |  | Tasks Done
| * Main App GUI | 3
* Tracker Connection
* Meetings @Parsiss
| • Total Hours | 3
@Parsiss
|  | @Home | 3