## Sheet1
Saeed Mohagheghi |  |  |  |  | Paid
Parsiss TimeSheet |  |  |  |  | Not Paid
خرداد 98 | Activity | Hours |  | Tasks Done
| * Reading Docs | 5 |  | • Preparing Python + QT Framework
| * PyQT Example Codes | 6 |  | • BronchoVision Initial GUI Design (PyQT)
| * BronchoVision GUI | 14
| * Python Tracker Connection | 5
| * Meetings @Parsiss | 4
| • Total Hours | 34
|  | @Parsiss | 9
|  | @Home | 25
تیر 98 | Activity | Hours |  | Tasks Done
| * Reading Docs | 6 |  | • Python Tracker Connection (Polaris)
| * BronchoVision GUI | 14 |  | • Load and Visualize Medical Images (mhd)
| * Python Tracker Connection | 23 |  | • Test Tracker Python Code in Linux (Ubuntu)
| * Meetings @Parsiss | 2
| • Total Hours | 45
|  | @Parsiss | 29
|  | @Home | 16
مرداد 98 | Activity | Hours |  | Tasks Done
| * OV Preparation & Build | 10 |  | • Python Tracker Connection (Aurora)
| * Reform OV GUI | 15 |  | • Build and Run OV GUI
| * Reading Docs | 1 |  | • Reform OV GUI
| * BronchoVision GUI | 4
| * Python Tracker Connection | 1
| * Meetings @Parsiss | 3
| • Total Hours | 34
|  | @Parsiss | 13
|  | @Home | 21
شهریور 98 | Activity | Hours |  | Tasks Done
| * Reform OV GUI | 3 |  | • Upgrade BronchoVision GUI
| * BronchoVision GUI | 3
| * BronchoVision Viewers | 4 |  | • Implement OV GUI Changes
| * Virtual Camera | 7
| • Total Hours | 17
|  | @Parsiss | 3
|  | @Home | 14